## Leveled totals
Bidder | Base bid | Plugs | Leveled total | Open gaps | Status | Bid file | Notes
Northgate Drywall & Acoustics | 752000 | 55800 | 807800 | 1 | Incomplete | input-bid-northgate.md | Sales tax included. Valid 30 days.
Prairie Wall & Ceiling Co. | 803800 | 0 | 803800 | 0 | Complete | input-bid-prairie.md | Straight time, five-day weeks.
Ridgeline Interiors | 789500 | 32600 | 822100 | 0 | Complete | input-bid-ridgeline.md | Revised August 22, 9:10 a.m. from $781,000 at bid time. Leveled on the revision at the estimator's direction.
Lowest | Bidder |  | Amount
Base bid | Northgate Drywall & Acoustics |  | 752000
Complete leveled total | Prairie Wall & Ceiling Co. |  | 803800
Leveled total = base bid + plugs marked Carry "Yes" on the Plugs sheet. A bid is complete when every gap carries a plug. Suggested plugs are the highest price another bidder itemized for the same line; change the amount, or set Carry to "No", on the Plugs sheet. As of 2026-08-22. This is a comparison, not an award recommendation.

## Scope
Scope | Northgate Drywall & Acoustics | Prairie Wall & Ceiling Co. | Ridgeline Interiors
Metal stud framing | Included | Included $312,000 | Included
Gypsum board, Level 4 finish | Included | Included $326,200 | Included
Level 5 finish at lobby (Addendum 2) | Not mentioned | Included $14,600 | Included
Shaft wall | Included | Included $58,300 | Included
Sound attenuation batts | Included | Included $22,800 | Excluded: "Excludes insulation"
In-wall blocking | Included | Included $18,900 | Included
Exterior glass-mat sheathing | Excluded: "Exterior sheathing by others." | Included $41,200 | Included
Firestopping at this trade's penetrations | Unclear: "Fire caulking at head-of-wall joints per UL details." | Included $9,800 | Excluded: "Excludes insulation and firestopping."
Addenda | 1 (missing 2) | 1, 2 | 1, 2
Base bid | 752000 | 803800 | 789500

## Plugs
Bidder | Scope | Bid says | Plug | Source | Carry (Yes/No)
Northgate Drywall & Acoustics | Level 5 finish at lobby (Addendum 2) | Not mentioned | 14600 | Suggested: Prairie Wall & Ceiling Co. itemized $14,600 for this line | Yes
Northgate Drywall & Acoustics | Exterior glass-mat sheathing | Excluded: "Exterior sheathing by others." | 41200 | Suggested: Prairie Wall & Ceiling Co. itemized $41,200 for this line | Yes
Northgate Drywall & Acoustics | Firestopping at this trade's penetrations | Unclear: "Fire caulking at head-of-wall joints per UL details." |  | Open: ask the bidder what the wording covers | No
Ridgeline Interiors | Sound attenuation batts | Excluded: "Excludes insulation" | 22800 | Suggested: Prairie Wall & Ceiling Co. itemized $22,800 for this line | Yes
Ridgeline Interiors | Firestopping at this trade's penetrations | Excluded: "Excludes insulation and firestopping." | 9800 | Suggested: Prairie Wall & Ceiling Co. itemized $9,800 for this line | Yes

## Questions
Bidder | Question
Northgate Drywall & Acoustics | Your bid acknowledges Addendum 1. Confirm you received Addendum 2 and that your price covers it.
Northgate Drywall & Acoustics | Your bid doesn't mention level 5 finish at lobby (Addendum 2). Is it in your base bid? If not, what would you add?
Northgate Drywall & Acoustics | Your bid says "Exterior sheathing by others." Confirm your bid excludes exterior glass-mat sheathing, or give us an add price.
Northgate Drywall & Acoustics | Your bid says "Fire caulking at head-of-wall joints per UL details." Does your base bid include firestopping at this trade's penetrations?
Ridgeline Interiors | Your bid says "Excludes insulation". Confirm your bid excludes sound attenuation batts, or give us an add price.
Ridgeline Interiors | Your bid says "Excludes insulation and firestopping." Confirm your bid excludes firestopping at this trade's penetrations, or give us an add price.
Ridgeline Interiors | Your revised number came in the morning after bids closed. What changed from the $781,000 you sent at 1:52 p.m.?